## 00 Overview
Section | Sub-Section | Item / Task | Layer | Detail / Expected Result | Status | Assigned Dev | Priority | Sprint / Phase | Notes
Salon Management System — Implementation Tracker
Source: Implementation Guide + Technical Spec ¦ MERN + PWA ¦ Arnav + Precious
Sheet | Scope | Item Count | Primary Owner
01 Architecture-Foundation | MERN scaffold, merge-safe routing, branch schema, seeds, audit log | 21 | Arnav (scaffold) + shared routing contract
02 RBAC-User-Management | Step zero: roles, permissions, login, user mgmt, staff self-service views | 19 | Arnav
03 Masters-Settings | Service/Product/Tax/Customer (Arnav); Staff/Shift/Package/WA Template (Precious) | 24 | Split — see sheet
04 Bookings | Internal bookings Phase 1, conflict engine, walk-ins, billing handoff | 9 | Arnav
05 Billing-POS-Inventory | POS, invoices, stock deduct, commission entries, GST, inventory views | 11 | Precious
06 Attendance-Payroll | Punch attendance (Precious); commission engine + payroll run (Arnav) | 13 | Precious (attendance) + Arnav (payroll)
07 CRM-WhatsApp | Visit log, segmentation, customer profile (Arnav); WABA campaigns (Precious) | 13 | Arnav (CRM) + Precious (WhatsApp)
08 Packages | CustomerPackage sale/redemption, client interpretation gate | 7 | Precious
09 Reports-Dashboard | Owner dashboard + revenue/staff/retention (Arnav); attendance/inventory/package/campaign reports (Precious) | 12 | Split — see sheet
10 Phases-Acceptance | Phase 0-3 milestones, client open items, UAT criteria | 27 | Both
TOTAL TASKS |  | 156
MERGE-CONFLICT RULES
1. Arnav owns backend/routes/arnavRoutes.js + frontend/src/routes/arnavRoutes.jsx — Precious owns preciousRoutes equivalents.
2. Never edit the other dev's route aggregator; register new routes only in your own file.
3. Shared components have a single owner (noted in Notes column) — import, don't duplicate.
4. Customer model + CustomerSearchOrCreate.jsx = Arnav. Precious consumes APIs only.
5. ProductMaster = Arnav. Stock deduction logic = Precious billingService only.
6. Phase 0 scaffold merged by Arnav before Precious starts feature branches.
7. Cross-module contracts (bookingId handoff, invoice.paid event) documented in README — agree before coding.

## 01 Architecture-Foundation
Section | Sub-Section | Item / Task | Layer | Detail / Expected Result | Status | Assigned Dev | Priority | Sprint / Phase | Notes
1. TECHNOLOGY STACK
Stack | Monorepo | Project scaffold (backend/ + frontend/) | All | Root package.json scripts; backend Node+Express .js; frontend React+Vite .jsx; .env.example for MONGO_URI, JWT_SECRET, PORT. | Not Started | Arnav | Critical | Phase 0 | Precious clones after scaffold merged — do not scaffold in parallel.
Stack | Frontend | React 18 + Vite setup (frontend/) | Frontend | Single responsive codebase; PWA-ready vite-plugin-pwa config stub; mobile-first breakpoints. | Not Started | Arnav | Critical | Phase 0
Stack | Backend | Node.js + Express API setup (backend/) | Backend | REST API; folders: models/, routes/, controllers/, services/, middleware/, seeds/, utils/. | Not Started | Arnav | Critical | Phase 0
Stack | Database | MongoDB + Mongoose connection | DB | config/db.js; health check endpoint GET /api/health. | Not Started | Arnav | Critical | Phase 0
Stack | Auth | JWT auth (login, refresh pattern) | Backend | POST /api/auth/login; Bearer token; password_hash on User; POST /api/auth/me returns user + permissions. | Not Started | Arnav | Critical | Phase 0
Stack | Charts | Chart.js (or Recharts) integration | Frontend | Shared chart wrappers in frontend/src/components/charts/ for dashboard reuse. | Not Started | Arnav | Medium | Phase 2
Stack | PWA | vite-plugin-pwa manifest + service worker | Frontend | Installable PWA; add-to-homescreen; offline shell for login page only (Phase 2 polish). | Not Started | Precious | Medium | Phase 2 | Precious owns PWA files: vite.config PWA block, manifest icons — no overlap with Arnav pages.
2. FOLDER STRUCTURE & MERGE-SAFE ROUTING
Architecture | Route split | backend/routes/arnavRoutes.js | Backend | Arnav mounts all own module routes here; index.js only imports arnavRoutes + preciousRoutes. | Not Started | Arnav | Critical | Phase 0 | Avoids both devs editing routes/index.js.
Architecture | Route split | backend/routes/preciousRoutes.js | Backend | Precious mounts billing, attendance, packages, whatsapp routes here. | Not Started | Precious | Critical | Phase 0
Architecture | Route split | frontend/src/routes/arnavRoutes.jsx | Frontend | Lazy-loaded routes for auth, dashboard, bookings, CRM, payroll, reports (Arnav modules). | Not Started | Arnav | Critical | Phase 0
Architecture | Route split | frontend/src/routes/preciousRoutes.jsx | Frontend | Lazy-loaded routes for billing, attendance, packages, campaigns, inventory reports. | Not Started | Precious | Critical | Phase 0
Architecture | App shell | ERP shell layout (collapsible left nav) | Frontend | Layout.jsx, Sidebar.jsx, TopBar.jsx — Celeris/AIMS style; menu items driven by permissions API. | Not Started | Arnav | Critical | Phase 0 | Precious does not edit Layout/Sidebar — adds menu entries via permission seeds only.
Architecture | API client | frontend/src/api/client.js + module API files | Frontend | Axios instance with auth interceptor; split api/arnav/ and api/precious/ subfolders per owner. | Not Started | Arnav | High | Phase 0
Architecture | Branch schema | models/Branch.js | DB | Single branch seeded; branch_id on User, Booking, Invoice; schema supports multi-branch later. | Not Started | Arnav | High | Phase 0
Architecture | Error handling | Global error middleware + API response envelope | Backend | Consistent { success, data, message } shape; 4xx/5xx handlers. | Not Started | Arnav | Medium | Phase 0
Architecture | Transactions | Mongo multi-document transaction helper | Backend | utils/withTransaction.js for billing+package redemption+commission atomic writes. | Not Started | Precious | Critical | Phase 1 | Used primarily in billing/package flows owned by Precious.
Architecture | Audit log | models/AuditLog.js + write helper | Backend | Log stock overrides, discount overrides, package redemptions, payroll finalize, permission changes. | Not Started | Arnav | Medium | Phase 1
3. SEED DATA & DEV SETUP
Seeds | Branch | seed/branchSeed.js — default salon branch | DB | One active branch row for dev/staging. | Not Started | Arnav | High | Phase 0
Seeds | Roles | seed/rolePermissionSeed.js | DB | Seed Owner/CEO, Manager, Stylist, Massage/Spa Therapist + all Permission rows + RolePermission map. | Not Started | Arnav | Critical | Phase 0
Seeds | Owner user | seed/ownerUserSeed.js | DB | Default CEO login for dev; temp password in README (not committed). | Not Started | Arnav | High | Phase 0
Seeds | Demo data | seed/demoDataSeed.js (services, products, staff) | DB | Optional sample masters for UI dev after modules built. | Not Started | Both | Low | Phase 1 | Split: Arnav seeds services/products; Precious seeds staff/shifts — separate seed files.

## 02 RBAC-User-Management
Section | Sub-Section | Item / Task | Layer | Detail / Expected Result | Status | Assigned Dev | Priority | Sprint / Phase | Notes
STEP ZERO — ROLES & PERMISSIONS (BUILD BEFORE FEATURE MODULES)
RBAC | DB | models/Role.js | DB | Fields: name, description. Seed 4 roles: Owner/CEO, Manager, Stylist, Massage/Spa Therapist. | Not Started | Arnav | Critical | Phase 0
RBAC | DB | models/Permission.js | DB | Fields: module, action (view¦create¦edit¦delete¦approve). One row per module+action combo. | Not Started | Arnav | Critical | Phase 0
RBAC | DB | models/RolePermission.js | DB | Many-to-many role_id + permission_id; drives dynamic left-nav. | Not Started | Arnav | Critical | Phase 0
RBAC | DB | models/UserMenuOverride.js | DB | user_id, permission_id, granted boolean — CEO per-user permission override. | Not Started | Arnav | High | Phase 0
RBAC | DB | models/User.js | DB | name, phone, email, password_hash, role_id, branch_id, is_active, created_by, created_at. | Not Started | Arnav | Critical | Phase 0
RBAC | Backend | middleware/requirePermission.js | Backend | requirePermission(module, action) — 403 if missing; resolves RolePermission + UserMenuOverride. | Not Started | Arnav | Critical | Phase 0
RBAC | Backend | GET /api/auth/permissions (or /me) | Backend | Returns resolved permission set for session; frontend builds menu from this. | Not Started | Arnav | Critical | Phase 0
RBAC | Frontend | hooks/usePermission.js — hasPermission(module, action) | Frontend | Central helper; NO scattered if(role==='owner') checks across codebase. | Not Started | Arnav | Critical | Phase 0
RBAC | Frontend | PermissionContext.jsx | Frontend | Loads permissions at login; provides to Sidebar and route guards. | Not Started | Arnav | Critical | Phase 0
RBAC | Frontend | ProtectedRoute.jsx | Frontend | Redirect to login; optional module+action gate per route. | Not Started | Arnav | High | Phase 0
USER MANAGEMENT (OWNER/CEO ONLY)
User Mgmt | Backend | CRUD /api/users | Backend | Create user (name, phone, role); soft-deactivate (is_active=false); never hard-delete with history. | Not Started | Arnav | Critical | Phase 0
User Mgmt | Backend | PUT /api/users/:id/permission-overrides | Backend | CEO toggles individual UserMenuOverride rows. | Not Started | Arnav | High | Phase 1
User Mgmt | Backend | Temp password + invite stub | Backend | Auto-generate temp password on create; hook for WhatsApp invite (Precious wires sender later). | Not Started | Arnav | Medium | Phase 1
User Mgmt | Frontend | pages/users/UserList.jsx | Frontend | List users with role, status; Owner/CEO only. | Not Started | Arnav | High | Phase 1
User Mgmt | Frontend | pages/users/UserForm.jsx | Frontend | Create/edit user, role dropdown, activate/deactivate. | Not Started | Arnav | High | Phase 1
User Mgmt | Frontend | pages/users/UserPermissionOverrides.jsx | Frontend | Per-user permission toggle grid. | Not Started | Arnav | Medium | Phase 1
User Mgmt | Frontend | pages/auth/Login.jsx | Frontend | Phone/Email + Password; single login URL for all roles; post-login redirect by permissions. | Not Started | Arnav | Critical | Phase 0
STYLIST / THERAPIST SELF-SERVICE VIEWS
Staff Portal | Frontend | pages/staff/MyCalendar.jsx (view only) | Frontend | Stylist/Therapist sees own bookings calendar only. | Not Started | Arnav | Medium | Phase 1 | Uses booking API read-only; separate file from Precious attendance views.
Staff Portal | Frontend | pages/staff/MyEarnings.jsx | Frontend | Own commission/earnings view for Stylist/Therapist roles. | Not Started | Arnav | Medium | Phase 2

## 03 Masters-Settings
Section | Sub-Section | Item / Task | Layer | Detail / Expected Result | Status | Assigned Dev | Priority | Sprint / Phase | Notes
ARNAV — SERVICE, PRODUCT, TAX MASTERS
Service Master | DB | models/ServiceCategory.js, models/ServiceMaster.js | DB | Category: name. Service: category_id, name, duration_minutes, price, commission_slab_override_id, is_active. | Not Started | Arnav | Critical | Phase 1
Service Master | Backend | CRUD /api/service-categories, /api/services | Backend | routes/serviceRoutes.js in arnavRoutes. | Not Started | Arnav | Critical | Phase 1
Service Master | Frontend | pages/settings/services/ServiceList.jsx, ServiceForm.jsx | Frontend | Settings > Services; category filter; duration/price/commission override. | Not Started | Arnav | High | Phase 1
Product Master | DB | models/ProductMaster.js | DB | name, sku, unit, purchase_price, sale_price, current_stock, reorder_level, is_active. | Not Started | Arnav | Critical | Phase 1 | Precious reads stock via API in billing — does not edit this model.
Product Master | Backend | CRUD /api/products | Backend | Includes GET low-stock list for dashboard alerts. | Not Started | Arnav | Critical | Phase 1
Product Master | Frontend | pages/settings/products/ProductList.jsx, ProductForm.jsx | Frontend | Stock level display; reorder level field. | Not Started | Arnav | High | Phase 1
Tax/GST Master | DB | models/TaxMaster.js | DB | name, rate, applies_to (service¦product¦both), is_active. | Not Started | Arnav | High | Phase 1
Tax/GST Master | Backend | CRUD /api/taxes | Backend | Used by billing service (Precious consumes). | Not Started | Arnav | High | Phase 1
Tax/GST Master | Frontend | pages/settings/tax/TaxList.jsx, TaxForm.jsx | Frontend | Separate rates for services vs products. | Not Started | Arnav | Medium | Phase 1
PRECIOUS — STAFF, SHIFT, PACKAGE MASTERS
Staff Master | DB | models/StaffProfile.js, models/CommissionSlab.js | DB | StaffProfile: user_id, designation, specialization[], commission_slab_id, base_salary, shift_id, joining_date. CommissionSlab: name, type, rules_json. | Not Started | Precious | Critical | Phase 1
Staff Master | Backend | CRUD /api/staff, /api/commission-slabs | Backend | routes/staffRoutes.js in preciousRoutes; filter stylists by specialization for bookings API consumer. | Not Started | Precious | Critical | Phase 1
Staff Master | Frontend | pages/settings/staff/StaffList.jsx, StaffForm.jsx | Frontend | Link to User; specialization multi-select; salary, shift, commission slab. | Not Started | Precious | High | Phase 1
Shift/Attendance Rules | DB | models/ShiftMaster.js, models/AttendanceRule.js | DB | Shift: name, start_time, end_time. Rules: late_mark_minutes, leave_types json. | Not Started | Precious | High | Phase 1
Shift/Attendance Rules | Backend | CRUD /api/shifts, /api/attendance-rules | Backend | Feeds attendance + payroll deduction logic. | Not Started | Precious | High | Phase 1
Shift/Attendance Rules | Frontend | pages/settings/attendance/ShiftList.jsx, AttendanceRulesForm.jsx | Frontend | Settings > Attendance Rules. | Not Started | Precious | Medium | Phase 1
Package Master | DB | models/PackageMaster.js | DB | type (prepaid_bundle¦membership), validity_days, price, included_services json, credit_count, discount_logic_json. | Not Started | Precious | Critical | Phase 1
Package Master | Backend | CRUD /api/package-masters | Backend | routes/packageMasterRoutes.js | Not Started | Precious | Critical | Phase 1
Package Master | Frontend | pages/settings/packages/PackageMasterList.jsx, PackageMasterForm.jsx | Frontend | Define prepaid vs membership; credit count; discount logic JSON fields with UI helpers. | Not Started | Precious | High | Phase 1
ARNAV — CUSTOMER MASTER (CRM OWNER)
Customer Master | DB | models/Customer.js | DB | name, phone (unique), dob, anniversary_date, gender, tags[], preferred_stylist_id, notes, created_at. | Not Started | Arnav | Critical | Phase 1 | Precious uses GET/POST search API only in booking/billing screens.
Customer Master | Backend | CRUD /api/customers + GET /api/customers/search?q= | Backend | Quick search for booking/billing; auto-create on first visit endpoint. | Not Started | Arnav | Critical | Phase 1
Customer Master | Frontend | components/customers/CustomerSearchOrCreate.jsx | Frontend | Shared component imported by Arnav bookings + Precious billing (Arnav owns file). | Not Started | Arnav | Critical | Phase 1 | Single owner prevents merge conflicts on customer UI.
PRECIOUS — WHATSAPP TEMPLATE MASTER
WhatsApp Template | DB | models/WhatsAppTemplate.js | DB | name, trigger_type, message_body, is_active. | Not Started | Precious | High | Phase 1
WhatsApp Template | Backend | CRUD /api/whatsapp-templates | Backend | Owner/Manager only. | Not Started | Precious | High | Phase 1
WhatsApp Template | Frontend | pages/settings/whatsapp/TemplateList.jsx, TemplateForm.jsx | Frontend | Pre-approved message templates for campaigns. | Not Started | Precious | Medium | Phase 1

## 04 Bookings
Section | Sub-Section | Item / Task | Layer | Detail / Expected Result | Status | Assigned Dev | Priority | Sprint / Phase | Notes
BOOKINGS / APPOINTMENTS — PHASE 1 INTERNAL ONLY
Bookings | DB | models/Booking.js | DB | customer_id, branch_id, stylist_id, service_ids[], booking_date, start_time, end_time, status, source, created_by, notes. | Not Started | Arnav | Critical | Phase 1
Bookings | Backend | services/bookingConflictService.js | Backend | Stylist+date+time overlap check; return next available slot suggestion on conflict. | Not Started | Arnav | Critical | Phase 1
Bookings | Backend | CRUD /api/bookings + PATCH status | Backend | Status flow: booked→confirmed→in_progress→completed→no_show¦cancelled. Walk-in = start_time now. | Not Started | Arnav | Critical | Phase 1
Bookings | Backend | GET /api/bookings/availability | Backend | Query stylist_id, date — return free slots. | Not Started | Arnav | High | Phase 1
Bookings | Frontend | pages/bookings/BookingList.jsx | Frontend | Today queue view for receptionist; filter by status/stylist. | Not Started | Arnav | High | Phase 1
Bookings | Frontend | pages/bookings/BookingForm.jsx | Frontend | Customer search-or-create, multi-service, stylist filtered by specialization, date/time, notes. Large touch targets. | Not Started | Arnav | Critical | Phase 1
Bookings | Frontend | pages/bookings/BookingCalendar.jsx | Frontend | Optional calendar view per stylist/day. | Not Started | Arnav | Medium | Phase 1
Bookings | Integration | Link completed booking → billing handoff | Frontend | Button 'Create Invoice' passes booking_id to billing route (Precious billing reads query param). | Not Started | Arnav | High | Phase 1 | Contract: /billing/new?bookingId=xxx — Precious implements reader only.
PHASE 2 — ONLINE BOOKING (NOT NOW)
Online Booking | Flag | Customer self-booking web flow | All | Phase 2 — same slot engine, source=online. Do not build in Phase 1. | Deferred | Arnav | Low | Phase 3

## 05 Billing-POS-Inventory
Section | Sub-Section | Item / Task | Layer | Detail / Expected Result | Status | Assigned Dev | Priority | Sprint / Phase | Notes
BILLING / POS
Billing | DB | models/Invoice.js, models/InvoiceLineItem.js | DB | Invoice: totals, payment_mode, payment_status. LineItem: item_type, item_id, staff_id (per line!), package_redemption_id. | Not Started | Precious | Critical | Phase 1
Billing | Backend | services/billingService.js | Backend | Create invoice atomically: line items, stock deduct, package redemption, commission entries. | Not Started | Precious | Critical | Phase 1
Billing | Backend | POST /api/invoices | Backend | Supports split payment; GST line tax from TaxMaster; blocks product sale if insufficient stock. | Not Started | Precious | Critical | Phase 1
Billing | Backend | Stock deduction + Manager override | Backend | Decrement ProductMaster.current_stock; require approve permission to force override; AuditLog entry. | Not Started | Precious | Critical | Phase 1 | Calls Arnav's product API/internal model read — no edits to product routes.
Billing | Backend | Package redemption at billing | Backend | Reduce line to ₹0 or membership %; set package_redemption_id; decrement CustomerPackage.credits_remaining in transaction. | Not Started | Precious | Critical | Phase 1
Billing | Backend | models/CommissionEntry.js + write on invoice save | Backend | Per line staff_id commission accrual for flat/tiered types (threshold type deferred to payroll). | Not Started | Precious | High | Phase 1
Billing | Frontend | pages/billing/PosScreen.jsx | Frontend | Touchscreen-friendly POS: customer, line items, per-line staff, package toggle, payment split. Dead simple UX. | Not Started | Precious | Critical | Phase 1
Billing | Frontend | pages/billing/InvoiceList.jsx, InvoiceDetail.jsx | Frontend | GST-compliant invoice display/print view. | Not Started | Precious | High | Phase 1
Billing | Frontend | components/billing/PaymentSplitModal.jsx | Frontend | Cash + UPI + card split amounts. | Not Started | Precious | Medium | Phase 1
INVENTORY (OPERATIONAL)
Inventory | Backend | GET /api/inventory/stock-report | Backend | Current stock, reorder alerts — read from ProductMaster. | Not Started | Precious | High | Phase 1
Inventory | Frontend | pages/inventory/StockOverview.jsx | Frontend | Low stock highlights; link to product settings (Arnav's screen). | Not Started | Precious | Medium | Phase 1

## 06 Attendance-Payroll
Section | Sub-Section | Item / Task | Layer | Detail / Expected Result | Status | Assigned Dev | Priority | Sprint / Phase | Notes
PRECIOUS — ATTENDANCE
Attendance | DB | models/Attendance.js | DB | staff_id, date, punch_in_time, punch_out_time, status, remarks, punched_by. | Not Started | Precious | Critical | Phase 1
Attendance | Backend | POST /api/attendance/punch-in, /punch-out | Backend | One open punch-in per staff per day; admin punch on behalf logs punched_by. | Not Started | Precious | Critical | Phase 1
Attendance | Backend | GET /api/attendance/today, /api/attendance/summary | Backend | Staff on duty for dashboard; monthly summary for payroll. | Not Started | Precious | High | Phase 1
Attendance | Frontend | pages/attendance/PunchScreen.jsx | Frontend | Single Punch In/Out toggle; tablet-friendly; staff self-select. | Not Started | Precious | Critical | Phase 1
Attendance | Frontend | pages/attendance/AttendanceLog.jsx | Frontend | Manager view of daily/monthly attendance. | Not Started | Precious | High | Phase 1
ARNAV — PAYROLL & COMMISSION ENGINE
Commission | Backend | services/commissionService.js — calculateCommission(staff_id, period) | Backend | Strategies: threshold_bonus, flat_pct, tiered, flat_by_item_type from CommissionSlab.rules_json. | Not Started | Arnav | Critical | Phase 2
Commission | Backend | Commission Settings CRUD /api/commission-settings | Backend | Owner edits slab rules via UI config — not hardcoded. | Not Started | Arnav | High | Phase 2
Commission | Frontend | pages/settings/commission/CommissionSettings.jsx | Frontend | Edit multiplier, bonus %, tier breakpoints per slab. | Not Started | Arnav | High | Phase 2
Payroll | DB | models/PayrollRun.js, models/PayrollEntry.js | DB | Run: month, year, status (draft¦finalized¦paid). Entry: base_salary, commission_total, deductions, net_payable. | Not Started | Arnav | Critical | Phase 2
Payroll | Backend | services/payrollService.js | Backend | base + commission (incl. month-end threshold bonus) + attendance deductions from Precious's summary API. | Not Started | Arnav | Critical | Phase 2 | Consumes GET /api/attendance/summary — no edits to attendance files.
Payroll | Backend | POST /api/payroll/runs, PATCH finalize | Backend | Manager view-only; Owner finalizes. Slab changes don't retroactive finalized runs. | Not Started | Arnav | Critical | Phase 2
Payroll | Backend | Export payroll Excel/PDF | Backend | GET /api/payroll/runs/:id/export?format=xlsx¦pdf | Not Started | Arnav | High | Phase 2
Payroll | Frontend | pages/payroll/PayrollRunList.jsx, PayrollRunDetail.jsx | Frontend | Generate draft, review entries, finalize, export. | Not Started | Arnav | High | Phase 2

## 07 CRM-WhatsApp
Section | Sub-Section | Item / Task | Layer | Detail / Expected Result | Status | Assigned Dev | Priority | Sprint / Phase | Notes
ARNAV — CRM & VISIT LOG
Visit Log | Backend | Auto-create visit log on booking completed / invoice paid | Backend | Hook in booking status listener + billing callback event. visit date, services, staff, amount, rating. | Not Started | Arnav | High | Phase 1 | Event contract documented in README — Precious emits invoice.paid event from billingService.
CRM | DB | models/CustomerVisitLog.js (or embedded visits[]) | DB | visit_date, services, staff_ids, amount, feedback_rating. | Not Started | Arnav | High | Phase 1
CRM | Backend | GET /api/customers/:id/profile | Backend | Visit history, active packages (read from Precious API), preferences, tags. | Not Started | Arnav | High | Phase 1
CRM | Backend | services/customerSegmentationService.js | Backend | Nightly job: birthday this week, anniversary, inactive 45+/60+, high-value, package expiring. | Not Started | Arnav | High | Phase 2
CRM | Backend | Customer tags — manual vs system | Backend | tags[].type = manual¦system; system tags recomputed nightly. | Not Started | Arnav | Medium | Phase 2
CRM | Frontend | pages/crm/CustomerProfile.jsx | Frontend | Read view: history, packages, preferences; manual vs system tags visually distinct. | Not Started | Arnav | High | Phase 1
CRM | Frontend | pages/crm/SegmentList.jsx | Frontend | View segments with counts; launch campaign hands off to Precious campaign screen. | Not Started | Arnav | Medium | Phase 2
PRECIOUS — WHATSAPP AUTOMATION
WhatsApp API | External | Meta WhatsApp Business API application | External | Start business verification immediately — longest lead time. Document WABA credentials in .env. | Not Started | Precious | Critical | Phase 1 | Parallel track — not blocked on code.
WhatsApp | DB | models/WhatsAppCampaignLog.js, models/MessageQueue.js | DB | Queue table for scheduled sends; log sent/delivered/read/failed. | Not Started | Precious | High | Phase 2
WhatsApp | Backend | services/whatsappService.js | Backend | Cloud API send; template variable substitution. | Not Started | Precious | Critical | Phase 2
WhatsApp | Backend | jobs/campaignScheduler.js | Backend | Cron: birthday, anniversary, appointment reminders, package expiry, win-back. Async — not sync from UI. | Not Started | Precious | Critical | Phase 2
WhatsApp | Backend | POST /api/campaigns/preview, POST /api/campaigns/send | Backend | Preview audience count; queue campaign messages. | Not Started | Precious | High | Phase 2
WhatsApp | Frontend | pages/crm/CampaignScreen.jsx | Frontend | Select trigger, template, preview count, schedule/send now. Owner/Manager only. | Not Started | Precious | High | Phase 2

## 08 Packages
Section | Sub-Section | Item / Task | Layer | Detail / Expected Result | Status | Assigned Dev | Priority | Sprint / Phase | Notes
PACKAGE SALE & REDEMPTION
Packages | DB | models/CustomerPackage.js | DB | customer_id, package_master_id, purchase_date, expiry_date, credits_remaining, status, invoice_id. | Not Started | Precious | Critical | Phase 1
Packages | Backend | POST /api/customer-packages/sale | Backend | Create CustomerPackage with expiry + credits from PackageMaster. | Not Started | Precious | Critical | Phase 1
Packages | Backend | GET /api/customers/:id/packages/active | Backend | List active packages/credits for billing redemption UI. | Not Started | Precious | Critical | Phase 1
Packages | Frontend | pages/packages/PackageSale.jsx | Frontend | Customer, package select, payment — creates CustomerPackage. | Not Started | Precious | High | Phase 1
Packages | Frontend | pages/packages/CustomerPackageList.jsx | Frontend | View active/expired/exhausted packages per customer. | Not Started | Precious | Medium | Phase 1
Packages | Business rule | Confirm package interpretation with client | All | Before redemption logic: single-service bundle vs credit pool vs straight discount. See Technical Spec §4. | Blocked | Both | Critical | Phase 1 | Client meeting item — do not guess.
Packages | Backend | Expiry/low-credit alert triggers | Backend | Emit events for WhatsApp scheduler when credits low or expiry within N days. | Not Started | Precious | Medium | Phase 2

## 09 Reports-Dashboard
Section | Sub-Section | Item / Task | Layer | Detail / Expected Result | Status | Assigned Dev | Priority | Sprint / Phase | Notes
ARNAV — DASHBOARD (SHOWSTOPPER)
Dashboard | Frontend | pages/dashboard/OwnerDashboard.jsx | Frontend | Hero greeting, business-health score, KPI cards, charts — executive cockpit style. | Not Started | Arnav | Critical | Phase 2
Dashboard | Backend | GET /api/dashboard/kpis | Backend | Today's revenue, bookings, walk-ins vs appointments, active packages, staff on duty — aggregates from both modules. | Not Started | Arnav | Critical | Phase 2
Dashboard | Frontend | pages/dashboard/ReceptionistDashboard.jsx | Frontend | Today's booking queue + quick billing shortcut only. | Not Started | Arnav | High | Phase 1
Dashboard | Frontend | Chart widgets — revenue trend, category split, staff leaderboard, booking funnel | Frontend | Recharts/Chart.js components in components/dashboard/. | Not Started | Arnav | High | Phase 2
ARNAV — REPORTS
Reports | Backend+Frontend | Revenue Report (daily/monthly, services vs products) | All | pages/reports/RevenueReport.jsx + GET /api/reports/revenue. Date range filter, Excel/PDF export. | Not Started | Arnav | High | Phase 2
Reports | Backend+Frontend | Staff Performance Report (leaderboard) | All | pages/reports/StaffPerformanceReport.jsx + GET /api/reports/staff-performance. | Not Started | Arnav | High | Phase 2
Reports | Backend+Frontend | Customer Retention Report | All | Repeat vs new, churn/inactive list. pages/reports/RetentionReport.jsx. | Not Started | Arnav | Medium | Phase 2
PRECIOUS — REPORTS
Reports | Backend+Frontend | Attendance Summary Report | All | pages/reports/AttendanceReport.jsx + GET /api/reports/attendance. | Not Started | Precious | High | Phase 2
Reports | Backend+Frontend | Inventory Stock / Reorder Report | All | pages/reports/InventoryReport.jsx + GET /api/reports/inventory. | Not Started | Precious | High | Phase 2
Reports | Backend+Frontend | Package Sales & Redemption Report | All | pages/reports/PackageReport.jsx + GET /api/reports/packages. | Not Started | Precious | Medium | Phase 2
Reports | Backend+Frontend | Campaign Performance Report | All | WhatsApp open/response if API provides. pages/reports/CampaignReport.jsx. | Not Started | Precious | Medium | Phase 2
Reports | Shared | components/reports/ReportFilterBar.jsx + exportUtils.js | Frontend | Date range, staff filter, category filter, Excel/PDF export. Precious owns file; Arnav imports. | Not Started | Precious | High | Phase 2 | Single owner for shared report components.

## 10 Phases-Acceptance
Section | Sub-Section | Item / Task | Layer | Detail / Expected Result | Status | Assigned Dev | Priority | Sprint / Phase | Notes
PHASE 0 — FOUNDATION (WEEK 1)
Phase 0 | Foundation | Scaffold + DB + Auth + RBAC seeds | All | Arnav delivers; Precious reviews PR before branching. | Not Started | Arnav | Critical | Phase 0
Phase 0 | Foundation | Route split (arnavRoutes / preciousRoutes) merged | All | Both devs can mount modules without touching same router file. | Not Started | Both | Critical | Phase 0
Phase 0 | Done When | Owner logs in; sees role-based menu; User CRUD works | All | Exit criteria Phase 0. | Not Started | Arnav | Critical | Phase 0
PHASE 1 — CORE OPS (WEEK 2-5)
Phase 1 | Masters | All Phase 1 masters seeded and CRUD working | All | Arnav: services, products, tax, customers. Precious: staff, shifts, package masters, WA templates. | Not Started | Both | Critical | Phase 1
Phase 1 | Transactions | Internal booking end-to-end | All | Create booking → conflict check → status updates → handoff to billing. | Not Started | Arnav | Critical | Phase 1
Phase 1 | Transactions | POS billing end-to-end | All | Invoice with services+products, stock deduct, package redemption, split payment, GST invoice. | Not Started | Precious | Critical | Phase 1
Phase 1 | Transactions | Attendance punch + package sale | All | Punch in/out; sell package; redeem at POS. | Not Started | Precious | Critical | Phase 1
Phase 1 | Done When | Front-desk can book, bill, punch, sell package in one day flow | All | Exit criteria Phase 1. | Not Started | Both | Critical | Phase 1
PHASE 2 — PAYROLL, CRM, REPORTS, DASHBOARD (WEEK 6-9)
Phase 2 | Payroll | Monthly payroll run with commission + attendance deductions | All | Threshold bonus at month-end; export Excel/PDF. | Not Started | Arnav | Critical | Phase 2
Phase 2 | CRM | Segmentation + visit log + customer profile complete | All | Inactive tags, birthday segments visible. | Not Started | Arnav | High | Phase 2
Phase 2 | WhatsApp | Automated campaigns live (至少 appointment reminder + birthday) | All | Queue-based send via Business API. | Not Started | Precious | High | Phase 2
Phase 2 | Dashboard | Owner dashboard 'showstopper' complete | All | All KPI cards and charts populated with real data. | Not Started | Arnav | Critical | Phase 2
Phase 2 | Reports | All 7 report types exportable | All | Revenue, staff, attendance, inventory, retention, packages, campaigns. | Not Started | Both | High | Phase 2
Phase 2 | Done When | Owner sees full dashboard; payroll finalized; WhatsApp birthday campaign sent | All | Exit criteria Phase 2. | Not Started | Both | Critical | Phase 2
PHASE 3 — FUTURE (POST CLIENT SIGN-OFF)
Phase 3 | Online booking | Customer-facing booking web/PWA | All | source=online into same slot engine. | Deferred | Arnav | Medium | Phase 3
Phase 3 | Biometric attendance | InsightFace / biometric punch | All | Reuse Celeris HRMS pattern if client wants upsell. | Deferred | Precious | Low | Phase 3
Phase 3 | Receptionist role | Seed Receptionist role + permissions | All | If client hires dedicated front-desk staff. | Deferred | Arnav | Low | Phase 3
CLIENT MEETING — OPEN ITEMS
Client | Discovery | Exact service list & pricing for seed data | All | Service Master seed. | Blocked | Both | Critical | Phase 1
Client | Discovery | Current system: manual vs existing software? | All | Migration effort estimate. | Blocked | Both | High | Phase 1
Client | Discovery | Staff count for commission/payroll estimate | All |  | Blocked | Both | High | Phase 1
Client | Discovery | Customer-facing booking in Phase 1? | All | Validate internal-first assumption. | Blocked | Both | Medium | Phase 1
Client | Discovery | WhatsApp number: new business vs existing | All | WABA setup. | Blocked | Precious | High | Phase 1
Client | Discovery | Package interpretation: buy 2 get 1 free example | All | Real rupee amounts + service names before redemption build. | Blocked | Both | Critical | Phase 1
ACCEPTANCE CRITERIA (UAT)
UAT | Security | Receptionist API direct call returns 403 for reports | Backend | Server-side RBAC enforced — not just hidden menu. | Not Started | Arnav | Critical | Phase 2
UAT | Billing | Multi-stylist invoice attributes commission per line | Backend | InvoiceLineItem.staff_id per line verified. | Not Started | Precious | Critical | Phase 1
UAT | Packages | Redemption audit trail links invoice line to CustomerPackage | Backend | No silent credit decrement. | Not Started | Precious | Critical | Phase 1
UAT | UX | Booking + billing completable in minimal taps on tablet | Frontend | Front-desk usability sign-off with client. | Not Started | Both | Critical | Phase 2