## 00 Overview
Section | Sub-Section | Item / Task | Layer | Detail / Expected Result | Status | Assigned Dev | Priority | Sprint / Phase | Notes
Leave + Holidays + Payroll — Implementation Tracker
Source: Leave-Clash-Swap-Implementation-Guide.docx + Attendance-Leave-Holidays-Payroll-Patch-Guide.docx ¦ Heramb ¦ August 2026
Build order is fixed — do not skip stages. Leave guide Stages 1-7 first; then Payroll patch Stages A-E; then frontend.
Sheet | Scope | Item Count | Primary Owner
01 Leave-Clash-Swap | weekly_off_day, LeaveRequest, clash, is_paid, swap, Attendance sync, leave APIs | 28 | Arnav
02 Attendance-Holidays-Payroll | Holiday model, attendance summary patch, PayrollRun/Entry, payrollService, payroll+holiday APIs | 22 | Arnav
03 Frontend-UAT | Leave apply/approve/swap UI, holiday settings, payroll pages, MyEarnings, dry-run UAT | 16 | Arnav
TOTAL TASKS |  | 66
BUILD RULES
1. Implement Leave guide Stages 1-7 before any Payroll patch stage.
2. Test each stage (REPL/Postman) before moving to the next — match Flowgenix trace-before-fix.
3. Leave routes mount in preciousRoutes.js next to attendance (per Leave guide). Payroll mounts where payroll was planned (arnavRoutes.js).
4. Blackout rule lives in exactly one place: backend/constants/leaveConstants.js.
5. Fri/Sat/Sun overrides everything — never a valid off date.
6. Payroll is direct-pay only: base_salary - unpaid-day deduction + commission. No tax slabs.
7. Dry-run one employee one month by hand before trusting net_payable on real staff.
STATUS KEY
Not Started ¦ In Progress ¦ Blocked ¦ Done ¦ Verified

## 01 Leave-Clash-Swap
Section | Sub-Section | Item / Task | Layer | Detail / Expected Result | Status | Assigned Dev | Priority | Sprint / Phase | Notes
STAGE 1 — WEEKLY OFF + BLACKOUT RULE
Leave | DB | StaffProfile.weekly_off_day field | DB | Number 1=Mon..4=Thu; default 1; validator rejects 0/5/6 (Sun/Fri/Sat). | Done | Arnav | Critical | Leave Stage 1 | Replace frontend-only Sunday weekly-off assumption.
Leave | Backend | constants/leaveConstants.js | Backend | BLACKOUT_DAYS=[5,6,0]; ALLOWED_DAYS=[1,2,3,4]; isBlackoutDate(dateObj). | Done | Arnav | Critical | Leave Stage 1 | Single source of truth — import everywhere.
Leave | Test | Reject weekly_off_day=5; accept=2 | Test | Model validator rejects Fri; accepts Tue. | Verified | Arnav | Critical | Leave Stage 1 | Manual Compass/shell or seed script.
STAGE 2 — LEAVEREQUEST MODEL
Leave | DB | models/LeaveRequest.js | DB | staff_id, date (UTC midnight), leave_type enum weekly_off¦extra_leave¦swapped_off, status pending¦approved¦rejected¦cancelled, is_paid, swap_with_staff_id, reason, approved_by. | Done | Arnav | Critical | Leave Stage 2
Leave | DB | Unique index {staff_id | date} | DB | Mongo rejects second leave same staff same day. | Done | Arnav | Critical | Leave Stage 2
Leave | DB | Index {date | status} | DB | Supports clash queries and calendar list. | Done | Arnav | High | Leave Stage 2
Leave | Test | Insert one LeaveRequest; duplicate fails | Test | Unique index confirmed in Compass/shell. | Verified | Arnav | Critical | Leave Stage 2 | npm run test:leave-request-unique
STAGE 3 — CLASH CHECKER
Leave | Backend | services/leaveClashService.js — normalize() | Backend | Normalize dates to UTC midnight for comparisons. | Done | Arnav | Critical | Leave Stage 3
Leave | Backend | checkClash({ staffId | date | excludeStaffId }) | Backend | 1) blackout Fri/Sat/Sun → blocked; 2) same designation + approved leave same date → blocked; else allowed. | Done | Arnav | Critical
Leave | Test | Beautician clash on Tuesday | Test | Second Beautician same Tue → allowed:false; Stylist same Tue → true; any Sat → false. | Verified | Arnav | Critical | Leave Stage 3 | npm run test:leave-clash
STAGE 4 — DEDUCTION CALCULATOR
Leave | Backend | getWeekStart(date) Mon–Sun week | Backend | UTC Monday start of calendar week. | Not Started | Arnav | Critical | Leave Stage 4 | Add to leaveClashService.js.
Leave | Backend | calculateIsPaid({ staffId | date }) | Backend | Count approved leaves same staff same week; first → paid true; 2nd+ → false. | Not Started | Arnav | Critical | Leave Stage 4
Leave | Test | 2nd leave same week unpaid | Test | 1 approved this week → 2nd date same week is_paid false; next week true. | Not Started | Arnav | Critical | Leave Stage 4
STAGE 5 — LEAVE SWAP
Leave | Backend | services/leaveSwapService.js — swapLeave() | Backend | Check A→B date and B→A date via checkClash (with exclude); calculateIsPaid both; delete old; create swapped_off approved. | Not Started | Arnav | Critical | Leave Stage 5 | No Mongo transaction in v1 — known gap.
Leave | Test | Valid swap Mon↔Wed same designation free | Test | success:true; both records swapped_off approved. | Not Started | Arnav | Critical | Leave Stage 5
Leave | Test | Swap into blackout blocked | Test | Destination Fri/Sat/Sun → success:false; no writes. | Not Started | Arnav | Critical | Leave Stage 5
Leave | Test | Swap into designation clash blocked | Test | Target date already has same designation off → fail; no partial write. | Not Started | Arnav | High | Leave Stage 5
STAGE 6 — ATTENDANCE SYNC
Leave | DB | Attendance.leave_request_id field | DB | ObjectId ref LeaveRequest; default null. | Not Started | Arnav | Critical | Leave Stage 6 | Patch models/Attendance.js.
Leave | Backend | syncAttendanceForLeave(leaveRequest) | Backend | Upsert Attendance by staff_id+date; status on_leave; remarks Paid/Unpaid leave; set leave_request_id. | Not Started | Arnav | Critical | Leave Stage 6 | Call on every approval (and after swap creates approved rows).
Leave | Test | Approve leave creates Attendance on_leave | Test | Attendance row exists with leave_request_id linked. | Not Started | Arnav | Critical | Leave Stage 6
STAGE 7 — LEAVE API ROUTES
Leave | Backend | routes/leaveRoutes.js created | Backend | New leave route module. | Not Started | Arnav | Critical | Leave Stage 7
Leave | Backend | Mount leaveRoutes in preciousRoutes.js | Backend | Next to existing attendance routes per guide. | Not Started | Arnav | Critical | Leave Stage 7
Leave | Backend | POST /api/leave/request | Backend | Employee apply: checkClash + calculateIsPaid; save pending. | Not Started | Arnav | Critical | Leave Stage 7
Leave | Backend | POST /api/leave/:id/approve | Backend | Manager approve → approved + syncAttendanceForLeave. | Not Started | Arnav | Critical | Leave Stage 7
Leave | Backend | POST /api/leave/:id/reject | Backend | Manager reject → rejected; no Attendance write. | Not Started | Arnav | Critical | Leave Stage 7
Leave | Backend | POST /api/leave/swap | Backend | Calls swapLeave(); both land approved; sync Attendance both sides. | Not Started | Arnav | Critical | Leave Stage 7
Leave | Backend | GET /api/leave?staff_id=&month= | Backend | List leave for staff / calendar view. | Not Started | Arnav | High | Leave Stage 7
Leave | Test | Postman full leave happy path | Test | Request → approve → Attendance on_leave; clash reject; swap ok. | Not Started | Arnav | Critical | Leave Stage 7

## 02 Attendance-Holidays-Payroll
Section | Sub-Section | Item / Task | Layer | Detail / Expected Result | Status | Assigned Dev | Priority | Sprint / Phase | Notes
PREREQUISITE
Payroll | Gate | Leave Stages 1-7 complete | All | LeaveRequest + is_paid + Attendance on_leave sync working before Stage A. | Not Started | Arnav | Critical | Payroll Gate | Do not start Holidays/Payroll until Leave guide Done.
STAGE A — HOLIDAY MODEL
Holiday | DB | models/Holiday.js | DB | date (UTC midnight unique), name, branch_id null=all, is_active. | Not Started | Arnav | Critical | Payroll Stage A
Holiday | DB | Index {date | branch_id} | DB | Supports month range queries. | Not Started | Arnav | High | Payroll Stage A
Holiday | Test | Insert 2-3 holidays; duplicate date blocked | Test | Unique date index confirmed. | Not Started | Arnav | Critical | Payroll Stage A
STAGE B — ATTENDANCE SUMMARY PATCH
Attendance | Backend | Export getMonthlyAttendanceSummary helper | Backend | Shared helper used by summary route + payrollService. | Not Started | Arnav | Critical | Payroll Stage B | Patch attendanceRoutes.js (or extract service).
Attendance | Backend | Populate leave_request_id on summary query | Backend | is_paid available without N+1 queries. | Not Started | Arnav | Critical | Payroll Stage B
Attendance | Backend | Holiday-aware day loop | Backend | Holiday date skips present/leave/absent counting for that day. | Not Started | Arnav | Critical | Payroll Stage B
Attendance | Backend | Count paid vs unpaid leave days | Backend | on_leave + leave_request_ref.is_paid → daysPaidLeave else daysUnpaidLeave. | Not Started | Arnav | Critical | Payroll Stage B
Attendance | Backend | New payableDays formula | Backend | payableDays = present + late + half_day*0.5 + daysPaidLeave + holidayCount; unpaidDays = unpaidLeave + absent. | Not Started | Arnav | Critical | Payroll Stage B
Attendance | Backend | workingDaysInMonth | Backend | totalDaysInMonth - holidayCount. | Not Started | Arnav | Critical | Payroll Stage B
Attendance | Backend | GET /api/attendance/summary returns new fields | Backend | workingDaysInMonth, daysPaidLeave, daysUnpaidLeave, holidayCount, payableDays, unpaidDays. | Not Started | Arnav | Critical | Payroll Stage B
Attendance | Test | Hand-count one employee one month | Test | Seed holiday + paid leave + unpaid leave + presents; verify every returned field by hand. | Not Started | Arnav | Critical | Payroll Stage B
STAGE C — PAYROLL MODELS
Payroll | DB | models/PayrollRun.js | DB | month, year, status draft¦finalized, run_by, finalized_at; unique {month,year}. | Not Started | Arnav | Critical | Payroll Stage C
Payroll | DB | models/PayrollEntry.js | DB | payroll_run_id, staff_id, base_salary, working_days_in_month, payable_days, unpaid_days, per_day_rate, deduction_amount, commission_total, net_payable; unique run+staff. | Not Started | Arnav | Critical | Payroll Stage C
Payroll | Test | Unique indexes for run and entry | Test | Duplicate month/year run fails; duplicate staff in run fails. | Not Started | Arnav | Critical | Payroll Stage C
STAGE D — PAYROLL SERVICE
Payroll | Backend | services/payrollService.js — runPayrollForMonth() | Backend | Upsert draft PayrollRun; for each active staff: summary → perDayRate → deduction → commission accrued → net_payable upsert entry; link commissions paid. | Not Started | Arnav | Critical | Payroll Stage D | Direct-pay only.
Payroll | Backend | Formula per_day_rate | Backend | base_salary / workingDaysInMonth (holidays excluded from denominator). | Not Started | Arnav | Critical | Payroll Stage D
Payroll | Backend | Formula deduction + net | Backend | deduction = round(perDay * unpaidDays); net = base - deduction + commission_total. | Not Started | Arnav | Critical | Payroll Stage D
Payroll | Backend | Link CommissionEntry to run | Backend | Set payroll_run_id + status paid so not double-counted next month. | Not Started | Arnav | Critical | Payroll Stage D | Field already on CommissionEntry — behavior patch only.
Payroll | Backend | finalizePayrollRun(id) | Backend | status finalized + finalized_at; routes reject further calc unless reopen built. | Not Started | Arnav | Critical | Payroll Stage D
Payroll | Test | Upsert same month does not duplicate | Test | Second runPayrollForMonth updates same entries. | Not Started | Arnav | High | Payroll Stage D
STAGE E — PAYROLL + HOLIDAY ROUTES
Payroll | Backend | routes/payrollRoutes.js | Backend | New payroll API module. | Not Started | Arnav | Critical | Payroll Stage E
Payroll | Backend | Mount payroll routes (arnavRoutes) | Backend | Where payroll was already commented as planned. | Not Started | Arnav | Critical | Payroll Stage E | Confirm mount file vs Leave's preciousRoutes.
Payroll | Backend | POST /api/payroll/run | Backend | Body {month | year}; creates/updates draft run + entries. | Not Started | Arnav | Critical | Payroll Stage E
Payroll | Backend | GET /api/payroll/run/:id | Backend | Run + entries populated with staff name/designation. | Not Started | Arnav | Critical | Payroll Stage E
Payroll | Backend | POST /api/payroll/run/:id/finalize | Backend | Locks the run. | Not Started | Arnav | Critical | Payroll Stage E
Payroll | Backend | GET /api/payroll/staff/:staffId?month=&year= | Backend | Employee payslip for MyEarnings. | Not Started | Arnav | High | Payroll Stage E
Holiday | Backend | GET /api/holidays?month=&year= | Backend | List holidays for month — feeds summary + settings UI. | Not Started | Arnav | High | Payroll Stage E
Holiday | Backend | POST /api/holidays | Backend | Admin adds holiday date. | Not Started | Arnav | High | Payroll Stage E

## 03 Frontend-UAT
Section | Sub-Section | Item / Task | Layer | Detail / Expected Result | Status | Assigned Dev | Priority | Sprint / Phase | Notes
LEAVE FRONTEND
Leave | Frontend | Employee apply-leave form | Frontend | Pick date Mon-Thu; leave_type; reason; call POST /api/leave/request; show clash errors. | Not Started | Arnav | Critical | Frontend | Desktop and/or mobile PWA — confirm UX with lead.
Leave | Frontend | Manager approval screen | Frontend | List pending; approve/reject; show designation clash context. | Not Started | Arnav | Critical | Frontend
Leave | Frontend | Leave swap UI | Frontend | Select peer + dates; call POST /api/leave/swap; surface failure reasons. | Not Started | Arnav | High | Frontend
Leave | Frontend | Staff weekly_off_day in Employees form | Frontend | Owner sets Mon-Thu weekly off on Staff Master (alongside salary/targets). | Not Started | Arnav | High | Frontend
Leave | Frontend | Remove hardcoded Sunday weekly-off | Frontend | Replace isWeeklyOffDay Sunday assumption with StaffProfile.weekly_off_day. | Not Started | Arnav | High | Frontend | attendanceUtils.js + mobile attendance history.
Leave | Frontend | Mobile leave history (optional polish) | Frontend | Show approved/pending leaves on mobile Attendance alongside punch history. | Not Started | Arnav | Medium | Frontend | Extends earlier mobile attendance work.
HOLIDAY + PAYROLL FRONTEND
Holiday | Frontend | Holiday settings screen | Frontend | Admin CRUD list of holidays (name + date); uses GET/POST /api/holidays. | Not Started | Arnav | High | Frontend | Settings area.
Payroll | Frontend | Wire PayrollHome / RunPayroll placeholders | Frontend | Generate draft run; list entries; finalize. | Not Started | Arnav | Critical | Frontend | pages/payroll/* already stubbed.
Payroll | Frontend | MyEarnings.jsx payslip | Frontend | Point at GET /api/payroll/staff/:staffId?month=&year=. | Not Started | Arnav | High | Frontend
Payroll | Frontend | Mobile earnings shows net if needed | Frontend | Align mobile Earnings with payslip fields when API ready. | Not Started | Arnav | Medium | Frontend
UAT / DRY-RUN
UAT | Test | Leave blackout never allows Fri-Sun | Test | All leave/swap paths return blocked. | Not Started | Arnav | Critical | UAT
UAT | Test | Designation clash blocks same-day offs | Test | Two Beauticians cannot both be approved off same Mon-Thu date. | Not Started | Arnav | Critical | UAT
UAT | Test | 1st weekly off paid; 2nd unpaid | Test | Attendance remarks + is_paid + payroll unpaidDays agree. | Not Started | Arnav | Critical | UAT
UAT | Test | Holiday excluded from working days | Test | payableDays includes holidayCount; denominator excludes holiday. | Not Started | Arnav | Critical | UAT
UAT | Test | Hand-calc net_payable one employee one month | Test | Manually compute base - deduction + commission; match PayrollEntry before real staff run. | Not Started | Arnav | Critical | UAT | Required by Payroll guide §8.
UAT | Docs | Mark tracker rows Done → Verified | Process | Update Status column after each stage test passes. | Not Started | Arnav | Medium | UAT