## 00 Overview
Section | Sub-Section | Item / Task | Layer | Detail / Expected Result | Status | Assigned Dev | Priority | Sprint / Phase | Notes
Pending Client Changes — Implementation Tracker
Source: IMPLEMENTATION_GUIDE_PENDING_CHANGES.md (Tech Lead) ¦ Client 4-feature pack ¦ August 2026
Build order is fixed — Feature 1 then 2 then 3 then 4. Do not start Feature 4 payroll deduction until 4.7 open points are confirmed.
Sheet | Scope | Item Count | Primary Owner
01 Late-Buffer | StaffProfile late_mark_buffer_minutes; punch resolution; StaffForm/StaffList UI | 12 | Arnav
02 Customer-Import-CRM | Wipe dummy CRM; seed ~3000 client customers; import API; inactive-visit CRM alert; CRM lazy load | 32 | Arnav
03 Family-Wallet-Package | amount_wallet package type; family linking; POS rupee deduction; void restore | 21 | Arnav
04 Redo-Rework | RedoRequest flow; ₹0 redo invoice; stock reason redo; payroll product-cost cut | 23 | Arnav
TOTAL TASKS |  | 88
BUILD RULES (from tech-lead MD)
1. Touch ONLY live files mounted from backend/routes/index.js frontend/src/routes/index.jsx frontend-mobile/src/App.jsx. Never edit dead/legacy files listed in MD section 0.3.
2. Backend: thin routes + services/*.js. Money/stock writes go through withTransaction. Stock ONLY via stockService deductStock/addStock. Never trust client totals.
3. Auth: authenticate + requirePermission on every new route. Reuse existing modules (staff crm packages billing payroll). Do not invent new permission modules.
4. Frontend: new APIs under frontend/src/api/arnav or precious; re-export from api/index.js. Pages use module-hero-header user-table user-table-card status-card S21 teal. Do NOT use dead DataTable/FormField/Modal.
5. Register pages with guardedRoute in arnavRoutes.jsx or preciousRoutes.jsx matching existing module/action of that area.
6. UI must match the live app: teal hero header sharp corners user-primary-btn--hero. No new visual system.
7. Feature 2 data: wipe dummy customers first (npm run seed:clear-customers) then import repo-root Contacts-24-Aug-02-31.xlsx (~3007 rows; Full Name + Mobile 1-4). Primary phone = first mobile; unused mobiles + Email + Address MUST go into notes. Phone is the unique merge key. Do not commit that PII xlsx.
8. Named constants for client-tunable numbers: MAX_WALLET_FAMILY_MEMBERS=6 REDO_WINDOW_DAYS=7 inactive threshold query default 60 CUSTOMER_LIST_PAGE_SIZE=25. Do not scatter magic numbers.
9. After seeding ~3000 customers NEVER load the full CRM set into the browser. Paginated GET /customers + CrmHome Load more (lazy). POS/booking stay typeahead search. WhatsApp must not hydrate all customers.
STATUS KEY
Not Started ¦ In Progress ¦ Blocked ¦ Done ¦ Verified
OPEN POINTS (code defaults; flag for client)
F2 inactive threshold + import headers — handover doc docs/Feature-2-CRM-Client-Open-Points.md (default 60d; UI 30/45/60/90; Contacts column map). Desktop CRM only v1. CRM pageSize 25 lazy load.
F3 GST at wallet purchase not redemption; overspend pays difference; max 6 family members; no wallet refund.
F4 deduct redo_staff_id; cost = purchase_price snapshot; 7-day window; one redo per original service line.

## 01 Late-Buffer
Section | Sub-Section | Item / Task | Layer | Detail / Expected Result | Status | Assigned Dev | Priority | Sprint / Phase | Notes
FEATURE 1 — PER-EMPLOYEE LATE-MARK BUFFER
Late buffer | DB | StaffProfile.late_mark_buffer_minutes | DB | Number min 0 max 30 default null. null/unset = use salon default (10). Additive; no migration. | Done | Arnav | Critical | Feature 1 | backend/models/StaffProfile.js — include in toSafeObject.
Late buffer | Backend | resolveLateMarkMinutesForStaff() | Backend | If staff.late_mark_buffer_minutes is number (incl 0) use it; else getLateMarkMinutesForBranch(branchId). | Done | Arnav | Critical | Feature 1 | attendancePunchService.js — 0 is valid (any lateness is late); do not treat 0 as default.
Late buffer | Backend | resolvePunchInStatus uses staff override first | Backend | Call resolveLateMarkMinutesForStaff(targetStaff branchId) instead of branch-only lookup. | Done | Arnav | Critical | Feature 1 | Downstream 3-lates payroll unchanged — consumes status only.
Late buffer | Backend | staffRoutes whitelist + validate | Backend | PATCH/PUT StaffProfile accepts late_mark_buffer_minutes: integer 0–30 or null. 400 otherwise. | Done | Arnav | Critical | Feature 1 | Reuse existing staff update route. Permission already on staff edit.
Late buffer | Frontend | StaffForm late buffer field | Frontend | Numeric 0–30 optional. Placeholder Default (10 min). Blank submits null not 0. Place near shift/salary. Teal S21 form styles. | Done | Arnav | Critical | Feature 1 | frontend/src/pages/settings/staff/StaffForm.jsx — match existing StaffForm inputs.
Late buffer | Frontend | StaffList optional column | Frontend | Show Late buffer: N min or Default. Same user-table as rest of Settings. | Done | Arnav | High | Feature 1 | StaffList.jsx — trivial add if table already lists shift/salary.
Late buffer | Permission | Reuse staff:edit | All | Do not create a new permission module. Same usePermission gate as StaffForm save. | Done | Arnav | High | Feature 1 | No staff module in RBAC — reused settings¦employees create/edit/delete (Staff Master + /employees). Late buffer has no separate permission. GET /staff left open for POS/bookings.
Late buffer | Test | Staff A buffer 5 vs B 15 vs C blank | Test | Shift+7min: A late; B present; C present if default 10. | Done | Arnav | Critical | Feature 1 | Extended testPunchLateStatus.js — npm run test:punch-late-status.
Late buffer | Test | Blank vs 0 distinction | Test | Empty form → null (salon default). Explicit 0 → late immediately after shift start. | Done | Arnav | Critical | Feature 1 | Extended testPunchLateStatus.js — blank→null; 0→late at shift+1.
Late buffer | Test | Branch AttendanceRule still applies | Test | Staff with no override still uses branch/global AttendanceRule then hardcoded 10. | Done | Arnav | High | Feature 1 | Extended testPunchLateStatus.js — getLateMarkMinutesForBranch kept; null override uses branch rule.
Late buffer | UI | Match existing Staff Master theme | Frontend | Teal hero already on staff pages; new field uses same labels/inputs as joining_date/shift — no new card system. | Done | Arnav | High | Feature 1 | Live StaffForm form-group/form-control + form-hint; StaffList staff-meta-muted column. No new visual system.
Late buffer | UAT | Owner sets per-stylist buffers and punches | UAT | Owner confirms punch status matches each staff's minutes on next punch only (not retroactive). | Done | Arnav | High | Feature 1 | npm run test:uat-late-buffer-punch — A/B/C at +7; mid-month buffer change does not rewrite past Attendance.

## 02 Customer-Import-CRM
Section | Sub-Section | Item / Task | Layer | Detail / Expected Result | Status | Assigned Dev | Priority | Sprint / Phase | Notes
FEATURE 2 — CUSTOMER DB WIPE + ~3000 CLIENT SEED + IMPORT + INACTIVE CRM
Data prep | Ops | Confirm client customer file received | Ops | File at project root: Contacts-24-Aug-02-31.xlsx. Sheet contactbackup. ~3007 data rows (~3005 named / ~2999 with a mobile). Do not commit this PII file to git. | Done | Arnav | Critical | Feature 2 | Headers: SNo ¦ Full Name ¦ Email ¦ Address ¦ Mobile 1 ¦ Mobile 2 ¦ Mobile 3 ¦ Mobile 4. No dob/gender/last_visit in file.
Data prep | Ops | Wipe dummy / demo CRM customers | Ops | Run existing npm run seed:clear-customers — deletes dummy customers plus their bookings invoices packages WA campaigns. Does not touch users/staff/services/products. | Done | Arnav | Critical | Feature 2 | Ran npm run seed:clear-customers — CRM already empty (0 customers). Wipe script OK before real import.
Data prep | Ops | Verify CRM empty after wipe | Ops | GET /customers (or CRM UI) shows 0 rows. No leftover demo names. | Done | Arnav | Critical | Feature 2 | Verified Customer.countDocuments()=0 after wipe. Safe to proceed with schema + import.
Customer schema | DB | Customer import fields | DB | imported_last_visit_date Date; source enum app¦import default app; import_batch_id String; import_row_ref String. phone stays unique. | Done | Arnav | Critical | Feature 2 | backend/models/Customer.js — additive only; included in toSafeObject.
Customer schema | DB | CustomerImportBatch model | DB | file_name uploaded_by total_rows created/merged/skipped error_rows status processing¦completed¦failed timestamps. | Done | Arnav | Critical | Feature 2 | backend/models/CustomerImportBatch.js — registered in server.js.
Import API | Deps | xlsx + multer if missing | Backend | Install only if not already in backend/package.json. Copy existing multer memory+5MB+csv/xlsx filter from live routes if any. | Done | Arnav | High | Feature 2 | xlsx already present. Installed multer. Added middleware/customerImportUpload.js (memory 5MB csv/xlsx) — no prior multer in live routes.
Import API | Backend | customerImportService.parseCustomerImportFile | Backend | CSV/XLSX via xlsx. Support MD headers (name phone dob gender last_visit_date notes) AND client Contacts headers (Full Name Mobile 1-4 Email Address). Normalize primary phone to 10 digits; build notes from unused mobiles + email + address. | Done | Arnav | Critical | Feature 2 | backend/services/customerImportService.js — CUSTOMER_IMPORT_HEADER_ALIASES + normalizeImportPhone + buildImportNotes.
Import API | Backend | importCustomers row-by-row | Backend | Create batch processing. Invalid row → error_rows skip. New phone → create source import with notes holding unused mobiles + email + address. Existing phone → merge empty fields only never overwrite name/phone; if notes empty fill from unused mobiles/email/address. Per-row try/catch not one big transaction. | Done | Arnav | Critical | Feature 2 | customerImportService.importCustomers — smoke: seeds/testImportCustomersRow10.js
Import API | Backend | POST /api/customers/import | Backend | requirePermission crm edit; multer single file; sendSuccess batch summary. | Done | Arnav | Critical | Feature 2 | customerRoutes.js — POST /import before /:id; customerImportUpload.single(file).
Import API | Backend | GET /api/customers/import/:batchId | Backend | requirePermission crm view. Return batch counts + error_rows. | Done | Arnav | High | Feature 2 | customerRoutes.js — GET /import/:batchId before /:id.
Seed 3000 | Ops | Map client columns to parser | Ops | Map Contacts-24-Aug-02-31.xlsx → Customer: Full Name→name; phone=first non-empty of Mobile 1..4 (normalize / strip +91); REQUIRED: remaining Mobile 2–4 (unused) + Email + Address → notes (e.g. Alt phones: … ¦ Email: … ¦ Address: …); skip SNo. No dob/gender/last_visit_date → leave null. | Done | Arnav | Critical | Feature 2 | Locked in customerImportConstants.js + HEADER_ALIASES. File headers match; ~3007 rows / ~2999 with mobile.
Seed 3000 | Backend | Seed/import the ~3000 client customers | Backend | After wipe: import Contacts-24-Aug-02-31.xlsx via POST /customers/import (owner) OR npm run seed:client-customers pointing at that root path. Target ~3000 unique phones from Mobile columns. Report created/merged/skipped/errors. | Done | Arnav | Critical | Feature 2 | npm run seed:client-customers — created=2813 merged=143 skipped=51 total_rows=3007; customers_now=2813. CustomerImportBatch audit exists.
Seed 3000 | Test | Verify count and unique phones | Test | Customer.countDocuments ≈ unique Mobile phones in Contacts-24-Aug-02-31.xlsx. No duplicate phones. Sample Full Name + Mobile 1 match DB. Rows with no mobile go to error_rows / skipped. | Done | Arnav | Critical | Feature 2 | Verified: DB=2813=file unique phones; 0 dups; sample 5/5 match; skipped=51. node seeds/testClientCustomersSeedVerify.js
Inactive alert | Backend | getInactiveCustomers({thresholdDays}) | Backend | Latest paid/partial Invoice.billing_date per customer else imported_last_visit_date. Never-visited = inactive. Sort days_since desc. Default threshold 60. | Done | Arnav | Critical | Feature 2 | backend/services/crmAlertService.js — DEFAULT_INACTIVE_THRESHOLD_DAYS=60. Smoke: 2813 never-visited inactive at 60.
Inactive alert | Backend | GET /api/customers/inactive | Backend | Query threshold_days default 60. requirePermission crm view. | Done | Arnav | Critical | Feature 2 | customerRoutes.js — GET /inactive before /:id.
Frontend | API | arnav customersApi import + inactive | Frontend | importCustomers(FormData); getInactiveCustomers({thresholdDays}); getImportBatch. Re-export arnavApi. | Done | Arnav | Critical | Feature 2 | frontend/src/api/arnav/customersApi.js + arnav/index.js re-exports.
Frontend | UI | CrmImportCustomers.jsx | Frontend | Upload csv/xlsx; show created/merged/skipped + error table. module-hero-header + status-card. No preview step required v1. | Done | Arnav | Critical | Feature 2 | frontend/src/pages/crm/CrmImportCustomers.jsx — teal hero + crm-table; route in later row.
Frontend | UI | CrmInactiveCustomers.jsx | Frontend | Copy CrmPendingCredits structure. Table: Name Phone Last Visit Days Since. Threshold dropdown 30/45/60/90 re-fetches. | Done | Arnav | Critical | Feature 2 | frontend/src/pages/crm/CrmInactiveCustomers.jsx — crm-toolbar + crm-table; tab wire in next row.
Frontend | UI | CrmHome tab + Import button | Frontend | Inactive Customers tab sibling to pending credits pattern. Import Customers button → import route. Same CRM permission as CrmHome. | Done | Arnav | Critical | Feature 2 | crm view for tab; Import uses crm edit → /crm/import (route next row).
Frontend | Routes | guardedRoute CRM pages | Frontend | Inactive: crm view. Import: crm edit. arnavRoutes.jsx. | Done | Arnav | Critical | Feature 2 | /crm/inactive (view) + /crm/import (edit) in arnavRoutes.jsx.
Frontend | UI | Keep S21 CRM visual language | Frontend | Teal hero white cards user-table user-filter-btn. No new dashboard chrome. | Done | Arnav | High | Feature 2 | Import + inactive: module-hero, status-card, user-table, user-filter-btn thresholds; crm-import-dropzone in CrmHome.css. No mobile inactive screen.
Lazy load | Prompt | Tech-lead: do not hydrate ~3000 customers in FE | All | OPTIMISED APPROACH — After Contacts-24-Aug-02-31.xlsx is seeded (~3000), never GET/render the full customer collection. Server-paginate GET /customers with page + pageSize (default CUSTOMER_LIST_PAGE_SIZE=25 max 50) returning {items total page pageSize hasMore}. CrmHome loads page 1 only; a Load more button (existing crm-btn) appends the next page while hasMore. Search is server-side and resets to page 1 (debounce ~300ms). Toolbar Total customers = API total not rows.length. Inactive list uses the same page/hasMore pattern. POS + CustomerSearchOrCreate stay typeahead (searchCustomers min 2 chars) — do not list-all. WhatsApp offers must not receive a 3000-row array; select via search or a server audience query. Keep live crm-table / crm-btn styles; no new UI kit and no virtualizer library. | Done | Arnav | Critical | Feature 2 | Approach locked in .cursor/rules/crm-lazy-load.mdc + IMPLEMENTATION_GUIDE §2.6a. Build starts row 25 (CUSTOMER_LIST_PAGE_SIZE). Today still listCustomers({limit:100}).
Lazy load | Constants | CUSTOMER_LIST_PAGE_SIZE | Backend | Named constant 25 in backend/constants (customerConstants.js). Cap pageSize at 50. Do not raise listCustomers max to 3000. | Done | Arnav | Critical | Feature 2 | backend/constants/customerConstants.js — CUSTOMER_LIST_PAGE_SIZE=25, CUSTOMER_LIST_MAX_PAGE_SIZE=50, resolveCustomerListPageSize(). Wire in listCustomers next row.
Lazy load | Backend | Paginate listCustomers | Backend | listCustomers({search page pageSize}) uses skip/limit + countDocuments. Return {items total page pageSize hasMore}. Keep sort name:1. Unbounded find() is not allowed. | Done | Arnav | Critical | Feature 2 | customerService.listCustomers — skip/limit + countDocuments; max pageSize 50 via resolveCustomerListPageSize. Controller still returns items[] until row 27 envelope.
Lazy load | Backend | GET /customers paginated response | Backend | Query page (default 1) pageSize (default 25) search. sendSuccess data = {items: toSafeObject[] total page pageSize hasMore}. Backward-compat: if old clients expect a bare array document in Notes and prefer the new shape only. | Done | Arnav | Critical | Feature 2 | listCustomersHandler returns paginated envelope; customersApi documents + maps limit→pageSize. CrmHome consumer update row 28.
Lazy load | Frontend | CrmHome first page + Load more | Frontend | On mount fetch page 1. Append on Load more. Do not replace the table chrome. Disable button when !hasMore. Show Loading customers… only on first page not on append. | Done | Arnav | Critical | Feature 2 | CrmHome fetchCustomersPage — page 1 replace, Load more append; toolbar total from API; loadingMore separate from loading.
Lazy load | Frontend | Debounced server search resets page | Frontend | Search/Clear refetch page 1 (replace rows). Do not client-filter a huge in-memory list. | Done | Arnav | Critical | Feature 2 | CrmHome — 300ms debounced server search resets page 1; Clear/Enter/Search immediate; rows = API items only.
Lazy load | Frontend | Inactive + WhatsApp must not dump 3000 | Frontend | CrmInactiveCustomers paginates the same way. CrmWhatsAppOffers: typeahead/select current results or backend audience — never pass full customers[] of 3000. | Done | Arnav | High | Feature 2 | Inactive GET paginated {items,total,hasMore}; CrmInactiveCustomers Load more + server search; CrmWhatsAppOffers typeahead + server send recipients.
Lazy load | Test | 3000-row CRM first paint | Test | After seed: first GET /customers returns ~25 items + total≈unique phones. Network payload not 3000 docs. Load more fetches page 2. Search by name/phone returns a page not the whole DB. POS picker still typeahead-only. | Done | Arnav | Critical | Feature 2 | npm run test:crm-lazy-load — seeds/testCrmLazyLoad.js (requires seed:client-customers).
Test | Test | CSV 5-row import mix | Test | 2 new 2 merge 1 missing phone in error_rows; batch not crashed. Re-run same file → no duplicates. | Done | Arnav | Critical | Feature 2 | npm run test:import-csv-5row — seeds/testImportCustomersCsv5Row.js (MD 2.8).
Test | Test | Inactive vs real invoice | Test | Invoice 10 days ago not inactive at 60 even if imported date old. Import-only 100 days ago is inactive. No date at all is inactive. | Done | Arnav | Critical | Feature 2 | npm run test:inactive-vs-invoice — seeds/testInactiveVsInvoice.js (MD 2.8).
Open points | Client | Confirm threshold + file headers | Client | Default 60 days adjustable in UI. Parser headers from 2.4 unless client file differs. | Done | Arnav | High | Feature 2 | Handover: docs/Feature-2-CRM-Client-Open-Points.md + IMPLEMENTATION_GUIDE §2.7. Constants DEFAULT_INACTIVE_THRESHOLD_DAYS + CLIENT_CONTACTS_COLUMN_MAP.

## 03 Family-Wallet-Package
Section | Sub-Section | Item / Task | Layer | Detail / Expected Result | Status | Assigned Dev | Priority | Sprint / Phase | Notes
FEATURE 3 — FAMILY AMOUNT-WALLET PACKAGE
Wallet | Constants | packageConstants.js | Backend | MAX_WALLET_FAMILY_MEMBERS = 6 named constant. Single place to change. | Not Started | Arnav | High | Feature 3 | backend/constants/packageConstants.js
Wallet | DB | PackageMaster type amount_wallet + wallet_value | DB | enum prepaid_bundle¦membership¦amount_wallet. wallet_value Number default null. Do not reuse credit_count/discount_logic_json for this type. | Not Started | Arnav | Critical | Feature 3 | backend/models/PackageMaster.js + toSafeObject
Wallet | DB | CustomerPackage wallet + family | DB | wallet_balance Number default null. linked_family_customer_ids [ObjectId Customer]. Keep credits_remaining for other types. | Not Started | Arnav | Critical | Feature 3 | backend/models/CustomerPackage.js
Family | Backend | packageFamilyService add/remove | Backend | addFamilyMember: type must be amount_wallet; customer exists; not buyer; not already linked; max 6. removeFamilyMember pulls id; allowed after partial use. | Not Started | Arnav | Critical | Feature 3 | backend/services/packageFamilyService.js
Family | Backend | Family member routes | Backend | POST /:customerPackageId/family-members and DELETE .../:customerId. requirePermission packages edit. Mount on live packageRoutes (sale routes) not dead files. | Not Started | Arnav | Critical | Feature 3 | precious packageRoutes.js
Redemption | Backend | Eligible wallet packages | Backend | batchValidatePackageRedemptions also finds amount_wallet active not expired wallet_balance>0 where customer is buyer OR in linked_family_customer_ids. | Not Started | Arnav | Critical | Feature 3 | packageRedemptionService.js
Redemption | Backend | pricing mode wallet_deduct | Backend | deduction = min(lineTotal wallet_balance); remainingCharge = lineTotal - deduction. Invoice not rejected if remainingCharge > 0 — remainder via cash/UPI/card. | Not Started | Arnav | Critical | Feature 3 | Mirror existing full_cover/discount_pct switch in billingController.
Redemption | Backend | Decrement wallet in createInvoice txn | Backend | findOneAndUpdate $inc wallet_balance -deduction. If hits 0 set status exhausted. Same pattern as credits_remaining. | Not Started | Arnav | Critical | Feature 3 | billingService.js withTransaction
Redemption | Backend | GST at purchase not redemption | Backend | Wallet sale taxed like package purchase. Redemption lines tax_rate 0 like prepaid_bundle. Flag default for client. | Not Started | Arnav | High | Feature 3 | resolveTax package branch — one-line if client later wants GST on redeem.
Redemption | Backend | voidInvoice restores wallet | Backend | voidInvoice reverses wallet_balance the same way it reverses credits_remaining. | Not Started | Arnav | Critical | Feature 3 | Required by MD 3.7
Frontend | UI | PackageMasterForm third type | Frontend | Radio/select amount_wallet. Show name price wallet_value (default=price) validity_days is_active. Hide credits/included_services/discount JSON. Extend existing type switch. | Not Started | Arnav | Critical | Feature 3 | Match PackageMasterForm teal modal/theme already used.
Frontend | UI | PackageSale family panel | Frontend | After selling amount_wallet: search existing customers (searchCustomers) + findOrCreateCustomer. List members with remove. Max 6. | Not Started | Arnav | Critical | Feature 3 | Reuse POS customer picker patterns not a new design.
Frontend | UI | CustomerPackageList wallet display | Frontend | Show ₹ wallet_balance not credits. Family: N chip opens same family panel. | Not Started | Arnav | High | Feature 3 | Existing list page styles.
Frontend | UI | PosScreen wallet redeem | Frontend | getEligiblePackageForLine includes family wallets. Toggle shows Wallet applied -₹X remaining ₹Y. Remainder stays payable. Same POS cart chrome. | Not Started | Arnav | Critical | Feature 3 | PosScreen.jsx live only.
Frontend | API | Family + wallet API wrappers | Frontend | Thin wrappers under precious or packages API folder; re-export. | Not Started | Arnav | High | Feature 3
Frontend | Routes | No dead package pages | Frontend | Register only in live precious/arnav routes. Do not edit AppRoutes.jsx dead tree. | Not Started | Arnav | High | Feature 3 | MD 0.3
Test | Test | Sell wallet + family redeem | Test | A buys ₹10000; add B; B ₹450 service → balance 9550; line GST 0. | Not Started | Arnav | Critical | Feature 3 | MD 3.7
Test | Test | Overspend remainder | Test | Balance 200 service 500 → charge 300 via payment mode; wallet 0 exhausted. | Not Started | Arnav | Critical | Feature 3
Test | Test | Remove family member | Test | B no longer eligible at POS after remove. | Not Started | Arnav | High | Feature 3
Test | Test | Void restores wallet | Test | Void the ₹450 invoice → balance back to 10000. | Not Started | Arnav | Critical | Feature 3
Open points | Client | GST overspend max family refund | Client | Coded: GST at purchase; pay difference; max 6; refund out of scope. | Not Started | Arnav | High | Feature 3 | MD 3.6 — flag do not build refund.

## 04 Redo-Rework
Section | Sub-Section | Item / Task | Layer | Detail / Expected Result | Status | Assigned Dev | Priority | Sprint / Phase | Notes
FEATURE 4 — SERVICE REDO / REWORK (BUILD LAST)
Redo | Gate | Do not ship payroll cut on assumptions | Process | Constants coded with defaults but payroll deduction must not go live until client confirms 4.7 (who is charged window one-redo cost basis). | Not Started | Arnav | Critical | Feature 4 | Highest-risk money-on-paycheck change.
Redo | Constants | redoConstants.js | Backend | REDO_WINDOW_DAYS = 7. Expose via GET /redo/config so FE does not duplicate. | Not Started | Arnav | High | Feature 4 | backend/constants/redoConstants.js
Redo | DB | models/RedoRequest.js | DB | original_invoice_id original_line_item_id customer original_staff redo_staff redo_invoice status pending_approval¦approved¦rejected¦completed requested_by approved_by products_used[] total_product_cost payroll_run_id. | Not Started | Arnav | Critical | Feature 4 | New live model only.
Redo | DB | InvoiceLineItem.redo_request_id | DB | Optional ObjectId ref RedoRequest default null. | Not Started | Arnav | Critical | Feature 4
Redo | DB | PayrollEntry.redo_product_cost_deduction | DB | Number default 0. Shown in payroll UI with other deductions. | Not Started | Arnav | Critical | Feature 4
Redo | Backend | stockService reason redo | Backend | Add redo to ADJUSTMENT_REASONS. Complete path calls deductStock(... | 'redo') never mutate stock directly. | Not Started | Arnav | Critical | Feature 4
Redo | Backend | redoService createRedoRequest | Backend | Service line only. Window from invoice.billing_date. One non-rejected redo per line. status pending_approval. No invoice/stock yet. | Not Started | Arnav | Critical | Feature 4
Redo | Backend | approve / reject | Backend | approve: payroll edit; pending → approved. reject: no invoice/stock/payroll. complete later records visit. | Not Started | Arnav | Critical | Feature 4
Redo | Backend | completeRedoRequest in withTransaction | Backend | Snapshot purchase_price; deductStock redo; ₹0 paid invoice other/note; ₹0 service line staff redo_staff skip CommissionEntry; set products_used total_product_cost redo_invoice_id completed. | Not Started | Arnav | Critical | Feature 4 | Empty productsUsed → cost 0 still free redo invoice.
Redo | Backend | redoRoutes mounted live | Backend | POST/ GET / POST approve reject complete. Mount with billing-adjacent precious/arnav aggregator — not dead invoiceRoutes.js. | Not Started | Arnav | Critical | Feature 4 | MD 0.3
Redo | Backend | payrollService redo deduction | Backend | Sum completed RedoRequest redo_staff_id payroll_run_id null in month. net = base - unpaid + commission - redoProductCostDeduction. linkRedoDeductionsToPayrollRun like commissions. Draft recompute must not double-count. | Not Started | Arnav | Critical | Feature 4 | Read runPayrollForMonth fully before coding.
Frontend | API | precious/redo.js wrappers | Frontend | Thin create list approve reject complete getConfig. Re-export preciousApi. | Not Started | Arnav | Critical | Feature 4
Frontend | UI | InvoiceDetail Request Redo | Frontend | Button on service lines inside window. Form: reason redo staff default original. module-hero / existing invoice layout. Link original ↔ redo invoices. | Not Started | Arnav | Critical | Feature 4 | InvoiceDetail.jsx live.
Frontend | UI | RedoApprovals.jsx | Frontend | pending_approval table Approve/Reject. guardedRoute payroll edit. Teal hero user-table like RunPayroll. | Not Started | Arnav | Critical | Feature 4 | preciousRoutes.jsx
Frontend | UI | RedoComplete.jsx | Frontend | approved list; product picker like POS + qty; submit complete; show total cost that will hit next payroll. | Not Started | Arnav | Critical | Feature 4 | Reuse PosScreen product add UX not a new design system.
Frontend | UI | RunPayroll + MyEarnings line | Frontend | Redo product cost deduction -₹X next to existing unpaid/commission lines. Same typography as current payroll breakdown. | Not Started | Arnav | High | Feature 4 | desktop RunPayroll.jsx + mobile Earnings if it shows deductions.
Frontend | Routes | Register three redo pages | Frontend | preciousRoutes.jsx next to PosScreen/RunPayroll. Permissions billing edit / payroll edit as in MD. | Not Started | Arnav | Critical | Feature 4
Frontend | UI | S21 consistency | Frontend | Teal hero status-card user-table user-primary-btn--hero. No DataTable/Modal from dead components. | Not Started | Arnav | High | Feature 4
Test | Test | Window + one-redo | Test | 3-day-old line OK; 10-day reject. Second redo on same line reject unless first rejected. | Not Started | Arnav | Critical | Feature 4 | MD 4.8
Test | Test | Complete with products | Test | 2 products stock AuditLog reason redo; ₹0 invoice; total_product_cost = qty × purchase_price. | Not Started | Arnav | Critical | Feature 4
Test | Test | Payroll month include + no double | Test | PayrollEntry.redo_product_cost_deduction matches; net reflects cut. Draft re-run does not double. | Not Started | Arnav | Critical | Feature 4
Test | Test | Reject has no side effects | Test | Reject pending → no invoice no stock no payroll. | Not Started | Arnav | High | Feature 4
Open points | Client | Confirm 4.7 before production | Client | (a) redo_staff_id deducted default original editable (b) purchase_price (c) 7 days (d) service-only free no cut (e) one redo per line. | Not Started | Arnav | Critical | Feature 4 | Do not change defaults silently.